## Task_Table1
WBS | Name | Estimated_Work | Duration
1.1 | Prepare needs assessment | 160h | 4w
1.2 | Determine location | 80h | 4w
1.3 | Define budget | 20h | 1w
1.4 | Determine desired finish date | 4h | 1w
1.5 | Specify quality level | 4h | 1w
2.1 | Develop plans | 320h | 4w
2.2 | Obtain permits | 4h | 6w
2.3 | Finalize construciton documents | 80h | 1w
2.4 | Obtain bids | 8h | 3w
2.5 | Select GC | 16h | 2d
3.1 | Construct space | 480h | 12w
3.2 | Meet with GC and architect | 4h | .5d
3.3 | Document issues | 4h | .5d
3.4 | Monitor changes | 48h | 12w
3.5 | walkthrough | 16h | 1d
4.1 | Organize move | 120h | 3w
4.2 | Develop final timeline | 24h | 5d
4.3 | Hire moving company | 16h | 1w
4.4 | Identify issues | 8h | 1d
4.5 | Prep for move | 40h | 1w
4.6 | Move | 16h | 2d