## Task_Table1
WBS | Name | Estimated_Work | Duration | Resources
1.1 | Prepare needs assessment | 160h | 4w | Relo PM
1.2 | Determine location | 80h | 4w | Relo PM
1.3 | Define budget | 20h | 1w | Relo PM
1.4 | Determine desired finish date | 4h | 1w | Relo Assistant
1.5 | Specify quality level | 4h | 1w | Relo Assistant
2.1 | Develop plans | 320h | 4w | Architect
2.2 | Obtain permits | 4h | 6w | Relo Assistant
2.3 | Finalize construciton documents | 80h | 1w | Architect
2.4 | Obtain bids | 8h | 3w | office manager
2.5 | Select GC | 16h | 2d | Relo PM
3.1 | Construct space | 480h | 12w | Contractor
3.2 | Meet with GC and architect | 4h | .5d | Relo PM
3.3 | Document issues | 4h | .5d | Relo Assistant
3.4 | Monitor changes | 48h | 12w | Relo PM
3.5 | walkthrough | 16h | 1d | Relo PM
4.1 | Organize move | 120h | 3w | Office manager
4.2 | Develop final timeline | 24h | 5d | Relo PM
4.3 | Hire moving company | 16h | 1w | Relo Assistant
4.4 | Identify issues | 8h | 1d | Relo PM
4.5 | Prep for move | 40h | 1w | Office manager
4.6 | Move | 16h | 2d | Movers